## Prototype
|  | Subtotals |  |  |  |  | Prototyping week
| Task | Hours | Wholesale | Retail | Margin | Pre-project | 1 | 2 | Comments
Project Owner |  | 6 | 900 | 900 | 0 | 2 | 2 | 2
| Review w/ James | 2 | 300 | 300 | 0 | 2
| Weekly project review | 4 | 600 | 600 | 0 |  | 2 | 2
|  | 0 | 0 | 0 | 0
Salesperson |  | 3 | 450 | 450 | 0 | 3 | 0 | 0
| Create proposal | 2 | 300 | 300 | 0 | 2
| Pre-sales meetings | 1 | 150 | 150 | 0 | 1
|  | 0 | 0 | 0 | 0
Project Manager |  | 1.5 | 120 | 150 | 30 | 0.5 | 0.5 | 0.5
| Set up Git | 0 | 0 | 0 | 0
| Set up initial Basecamp project | 0.5 | 40 | 50 | 10 | 0.5
| Weekly task review | 1 | 80 | 100 | 20 |  | 0.5 | 0.5
|  | 0 | 0 | 0 | 0
Creative Director |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Graphic Artist |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Estimate review | 0 | 0 | 0 | 0
| Review build | 0 | 0 | 0 | 0
| Storyboards | 0 | 0 | 0 | 0
| Screen Mockups | 0 | 0 | 0 | 0
Lead Developer |  | 38 | 5700 | 5700 | 0 | 0 | 16 | 22
| Weekly review | 2 | 300 | 300 | 0 |  |  | 2
| Clarinet screens - sample page layout | 2 | 300 | 300 | 0 |  | 2
| Equipment screen - sample page layout | 2 | 300 | 300 | 0 |  | 2
| Mouthpiece screens - sample page layout | 2 | 300 | 300 | 0 |  | 2
| Musical terms - sample page layout | 3 | 450 | 450 | 0 |  | 3
| Tril charts | 3 | 450 | 450 | 0 |  | 3
| Add menu items for downloadable audio/video content | 2 | 300 | 300 | 0 |  | 2
| Add sample description pages for audio/video content | 2 | 300 | 300 | 0 |  | 2
| Research and choose CMS hosting solution | 4 | 600 | 600 | 0 |  |  | 4
| Provide three CMS options for client to try out | 2 | 300 | 300 | 0 |  |  | 2
| Refine CMS to deliver specific authenticated content | 4 | 600 | 600 | 0 |  |  | 4
| Create template that can be used in each CMS option | 4 | 600 | 600 | 0 |  |  | 4
| Audio library and playlist screens | 8 | 1200 | 1200 | 0 |  |  | 8
Secondary Developer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Static content for clarinet | 0 | 0 | 0 | 0 | 0
| Static content for trumpet | 0 | 0 | 0 | 0
| Static content for sax | 0 | 0 | 0 | 0
| Add support for PinchMedia | 0 | 0 | 0 | 0
| Bug fixes | 0 | 0 | 0 | 0
| CMS content for clarinet | 0 | 0 | 0 | 0
| CMS content for trumpet | 0 | 0 | 0 | 0
| CMS content for sax | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Quality Assurance Engineer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test Builds | 0 | 0 | 0 | 0 |  | 0 | 0
Build Manager |  | 2 | 40 | 300 | 260 | 0 | 0.5 | 1.5
| Set up device IDs | 0 | 0 | 0 | 0
| Weekly builds | 2 | 40 | 300 | 260 |  | 0.5 | 1.5
|  | 0 | 0 | 0 | 0
Bookkeeper |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Set up as client vendor | 0 | 0 | 0 | 0
| Invoicing | 0 | 0 | 0 | 0
| Set up in Freshbooks | 0 | 0 | 0 | 0
Project Totals |  |  |  |  | 0
| Project Total | 46.5 | 6610 | 6900 | 290
Rates |  |  | Wholesale | Retail
| Project Owner |  | 150 | 150 | 0
| Salesperson |  | 150 | 150 | 0
| Project Manager |  | 80 | 100 | 20
| Creative Director |  | 150 | 150 | 0
| Graphic Artist |  | 80 | 150 | 70
| Lead Developer |  | 150 | 150 | 0
| Secondary Developer |  | 25 | 50 | 25
| QA Engineer |  | 20 | 60 | 40
| Build Manager |  | 20 | 150 | 130
| Bookkeeper |  | 25 | 50 | 25

## Implementation
|  | Subtotals |  |  |  |  | Development week |  |  | Post-release
| Task | Hours | Wholesale | Retail | Margin | Pre-project | 1 | 2 | 3 | Bug fixes | Comments
Project Owner |  | 9 | 1350 | 1350 | 0 | 2 | 2 | 2 | 2 | 1
| Review w/ James | 2 | 300 | 300 | 0 | 2
| Weekly project review | 7 | 1050 | 1050 | 0 |  | 2 | 2 | 2 | 1
|  | 0 | 0 | 0 | 0
Salesperson |  | 3 | 450 | 450 | 0 | 3 | 0 | 0 | 0 | 0
| Create proposal | 2 | 300 | 300 | 0 | 2
| Pre-sales meetings | 1 | 150 | 150 | 0 | 1
|  | 0 | 0 | 0 | 0
Project Manager |  | 2.5 | 200 | 250 | 50 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| Set up Git | 0 | 0 | 0 | 0
| Set up initial Basecamp project | 0.5 | 40 | 50 | 10 | 0.5
| Weekly task review | 2 | 160 | 200 | 40 |  | 0.5 | 0.5 | 0.5 | 0.5
|  | 0 | 0 | 0 | 0
Creative Director |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Graphic Artist |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Estimate review | 0 | 0 | 0 | 0
| Review build | 0 | 0 | 0 | 0
| Storyboards | 0 | 0 | 0 | 0
| Screen Mockups | 0 | 0 | 0 | 0
Lead Developer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Weekly review | 4 | 600 | 600 | 0 |  |  | 2 | 2
|  | 0 | 0 | 0 | 0 |  |  |  |  | 0
Secondary Developer |  | 50 | 1250 | 2500 | 1250 | 0 | 2 | 28 | 16 | 4
| Static content for clarinet | 8 | 200 | 400 | 200 | 0 |  | 8
| Static content for trumpet | 8 | 200 | 400 | 200 |  |  | 8
| Static content for sax | 8 | 200 | 400 | 200 |  |  | 8
| Content for musical terms section | 4 | 100 | 200 | 100 |  |  | 4
| Add support for PinchMedia | 2 | 50 | 100 | 50 |  | 2
| Bug fixes | 8 | 200 | 400 | 200 |  |  |  | 4 | 4
| CMS content for clarinet | 4 | 100 | 200 | 100 |  |  |  | 4
| CMS content for trumpet | 4 | 100 | 200 | 100 |  |  |  | 4
| CMS content for sax | 4 | 100 | 200 | 100 |  |  |  | 4
|  | 0 | 0 | 0 | 0
Quality Assurance Engineer |  | 1 | 20 | 150 | 130 | 0 | 0 | 0 | 1 | 0
| Test Builds | 1 | 20 | 150 | 130 |  | 0 | 0 | 1 | 0
Build Manager |  | 5 | 100 | 750 | 650 | 0 | 0.5 | 1.5 | 2.5 | 0.5
| Set up device IDs | 0 | 0 | 0 | 0
| Weekly builds | 5 | 100 | 750 | 650 |  | 0.5 | 1.5 | 2.5 | 0.5
|  | 0 | 0 | 0 | 0
Bookkeeper |  | 0.5 | 12.5 | 25 | 12.5 | 0 | 0 | 0 | 0 | 0.5
| Set up as client vendor | 0 | 0 | 0 | 0
| Invoicing | 0.5 | 12.5 | 25 | 12.5 |  |  |  |  | 0.5
| Set up in Freshbooks | 0 | 0 | 0 | 0
Project Totals |  |  |  |  | 0
| Project Total | 64 | 2332.5 | 4425 | 2092.5
Rates |  |  | Wholesale | Retail
| Project Owner |  | 150 | 150 | 0
| Salesperson |  | 150 | 150 | 0
| Project Manager |  | 80 | 100 | 20
| Creative Director |  | 150 | 150 | 0
| Graphic Artist |  | 80 | 150 | 70
| Lead Developer |  | 150 | 150 | 0
| Secondary Developer |  | 25 | 50 | 25
| QA Engineer |  | 20 | 60 | 40
| Build Manager |  | 20 | 150 | 130
| Bookkeeper |  | 25 | 50 | 25